## Sheet1
Milesstone Description | Assigned | Date Start | Due date | Days | November |  |  |  | December |  |  |  | January |  |  |  | Febuary |  |  |  | March
[5 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Prototyping and Coding
Application Screen Design | ARMAN DOYOGAN | 2024-01-11 | 11/15/2024 | 15 | bar: November 1 to November 3
Modules | ALL TEAM MEMBERS
User Account Management | ALL TEAM MEMBERS | 2024-03-11 | 11/18/2024 | 16 | bar: November 1 to November 3
Algorithm Development | ALL TEAM MEMBERS | 11/20/2024 | 2024-03-12 | 12 | bar: November 3 to December 1
Route Selection Engine | ALL TEAM MEMBERS | 2024-01-12 | 12/31/2024 | 31 | bar: December 1 to December 4
Real-time Data Integration | ALL TEAM MEMBERS | 2025-01-01 | 02/28/2025 | 58 | bar: January 1 to Febuary 4
Notification and Alert System | ALL TEAM MEMBERS | 2025-01-02 | 2025-01-03 | 38 | bar: Febuary 1 to March 2
Testing
Alpha test |  | 03/20/2025 | 03/25/2025 | 6 | bar: March 3
Beta test |  | 03/25/2025 | 03/30/2025 | 5 | bar: March 4